## Vision & Definitions
Vision and Objectives
Vision:
In 2038, the village of Charvil will have emerged as a recognisable community with an improved quality of life for all its residents. It will have high quality, sustainable housing. The semi-rural nature of the village will remain and local green space and heritage assets will be protected and enhanced. People will walk and cycle more using new cycling and pedestrian routes in a safer road network. Charvil will be a resilient sustainable community which mitigates the effects of climate change and flooding. Delivery of the Vision will result in a stronger and more cohesive community.
Objectives:
To Protect and Enhance Green Space: Green spaces, waterways and countryside will be maintained and developed as a valued resource for Charvil. This will encourage a broad range of recreation and contribute to well-being by providing accessible routes to facilities, including for sports, walking, cycling and nature-based vistas. The natural habitat will support a broad diversity of thriving flora, fauna and fungi coexisting sustainably with all new housing developments,
To Improve Housing Choice: Charvil will become a recognisable community, improving the quality of life for all its residents through the provision of the right mix of high quality, sustainable accommodation.
To Stimulate Walking and Cycling: Charvil will improve the quality of life for its residents by mitigation of the adverse impacts of road traffic and successfully promoting active travel through provision of new integrated infrastructure including dedicated pathways and cycleways and public transport options. Road safety will be improved by the adoption of appropriate mitigations of traffic speeding and noise. Road safety will be increased for local children with the provision of defined walking and cycling routes to and from local schools
To improve Community Resilience: Charvil will help prevent any flooding in existing or future housing developments by maintaining local information on flooding to inform planning applications. It will increase community resilience through a re-established flood warden network and village flood response plan. It will proactively look to promote solar and other renewable energy sources in new developments.
To Build a Sustainable Community: Residents will use the opportunities presented by neighbourhood planning to strengthen the community in Charvil. The nature of the village and its sense of community is challenged by many of the issues identified in the previous themes. Ensure sustainability is at the heart of all development opportunities and plans.

## Village Projects 2026-2030
Charvil Five Year Plan 2026-31
Project | Priority | Reality | S/M/L | Comments | Description/Evidence | Estimated Cost | Lead Group | NP Link | Date Completed | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031
Full Council Projects | H/M/L | H/M/L | [7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Teenage facility (Pump track or other?) | H | H | Med | S106 agreement provisions for something Land challenge (on Hicks site or vale view | Teenage recreation facility e.g. Pump track location needs to be identified. Possible inclusion in future development of Hicks field | c £50-200k | Full Council | bar: 2026 Q4
Connectivity - Footpaths, highway improvements, safety, etc | H | M | S-M | Possible improvements from CIL and housing developers e.g. Bellway | Linked to planning comments |  | Full Council
Fishing |  |  |  | We have a way forwards here in short term support Charvil angling club Sorted in short term but not to everyone's liking |  |  | Full Council |  | 2026-06-26 | bar: 2026 Q2
Additional Allotments & Vegetable Patches | H | M | Med | Identify location for allotments. £60k cost estimate from WBC. Possible new allotment sites included as part of any Hicks Field development. S106 confirms this and provisions money for this We have a waiting list Work with WBC for this |  |  | Full Council | bar: 2027 Q4
Amenities Projects
MUGA Upgrade/Maintenance | H | H | Long | 10yr horizon for investment | The surface may need replacing sooner than the structure and fixtures as it was not well laid in the first instance | 60K | Amenities |  |  | 2027 Q1: Suggestion to move this to 2030
Tennis Courts | L | M | Med | Court maintenence including cleaning, re-colouring, re-lining and fence repairs | Review in 2028 for 2029/30 |  | Amenities | bar: 2028 Q1
Renovation of St Patrick's playground | M | M | Long | Well maintained; 5 to 10yr plan to update it - maybe interim upgrade | Renovation and expansion of childrens play ground at St Patricks | 100k | Amenities | bar: 2028 Q4
Sensory Garden (Dog Free) | M | H | Med | Hawthorns park already dog free - make more of that Identify basis for a sensory garden - possible area to left of EPF playground, but fencing costs may be prohibitive Other parishes we can learn from? Twyford theraputic garden (short term goal) | Small garden area kept dog free for younger and older residents. Resident survey desire no site identified. |  | Amenities
Pavillion Pre-school | L | L | Long | Pavillion is suitable for pre-school potentially, but NOT for nursery Pre-req of previous experience Wait for right opportunity to arise Need quick down select criteria in place | New purpose built building to provide base for preschool facility. Ofsted FAQ available for potential providers |  | Amenities
Upgrade Garden behind Pavillion | L | L | Long | Leave it and see what happens - ask Econet for a proposal | Fence in open area behind pavillion including improving access from pavillion back doors. Provide garden or secure play area for future pre school and other users Cubs/brownies? | tbc | Amenities |  | 2026-06-26 | bar: 2026 Q1
Benches/ picnic tables (St Pats and EPF) | H | H | Short | Done St Pats Consider for area behind EPF Play area Less contentious to put benches along side football pitches APRIL amenities | Completed |  | Amenities |  | 2026-06-26 | bar: 2026 Q2
Table Tennis/ Chess Boards (St Pats and EPF) | H | H | Short | April amentities | Completed |  | Amenities |  | 2026-06-26 | bar: 2026 Q2
Zip Wire (St Pats) | L | L | Long | Linked to broader provision at st pats |  |  | Amenities | bar: 2027 Q4
Jogging track | M | M | Med | Continue at St Pats | Needs to be considered as part of a broader strategy for facilities at St. Pats |  | Amenities | bar: 2027 Q4
East Park Farm Cricket Netting | H | H | S | Complete but needs better netting | Simple solution for preventing balls going into stream. Approved at May amenities meeting. | £750 | Amenities |  | 2026-06-26
Outdoor Gym | M | M | Med | Outdoor gym facility at EPF or St Pat's Could link to teenage provision not too onerous should investigate viability Linked to MUGA enhancement |  |  | Amenities | bar: 2027 Q4
Solar Panels on Pavillion | H | M | S-M | Business Case needs to support investment - but if there is a case Wokingham restrictions need consideration and cause a no last time - check with Lee Pavillion could be an asset we look to take on? Should we revisit this? Miranda to re-share legal advice | Quote from Solar together obtained. Ascertaining suitability of pavillion to host survey booked for November. Quote of 11300 GBP under consideration may delay and await costs reduction. | £10k | Amenities, then Full Council | bar: 2027 Q2
East Park Farm Sporting Pitch Fence | H | H | Med | Need to have one 3yr plan and build up reserves in budget | Replacement of existing either woooden or less expensive alternative | £12k | Amenities, then Full Council | bar: 2026 Q3
Tree Surveys - EPF, St. Pats, Village Hall |  |  |  | Last surveys were done in August 2024 with works completed in 2025. Next survey due in 2028 | Survey cost plus remedial work | £1,200+ | Amenities, then Full Council | bar: 2028 Q2
Working Group Feasibility Research | bar: 2027 Q4
Asset Transfer | H | S | Short | Working Group research to identify potential assets for transfer e.g. Hawthorns and Vale View Playgrounds, Pavilion | Investigate willingness of Wokingham to idscuss asset transfer opportunities. Working Group initially to look at potential assets for transfer and the feasibility, in conjunction with Wokingham | Unknown at this stage | Working Group (viability research) | bar: 2026 Q4
Land Purchase | M | M | Med | Would be interested if the right piece of land came up ongoing horizon scan. There may also be opportunities to discuss transfer of Wokingham owned land to CPC | Opportunistic purchase of land when available. | Unknown at this stage | Working Group (viability research) | bar: 2029 Q1
Community Café (permanent or mobile) - viability assessment | H | M | Short | A proper project - needs driving and external help/support from community and others Short term viability assessment - in 5yr plan Needs a working group - hence medium reality | Community café NP resident survey provides strong desire. No site identified or plans. | Unknown at this stage | Working Group (viability research) | bar: 2028 Q4
Connectivity - Charvil to Twyford Greenway (Cycle Path) | H | L | Long | Cannot be a parish council undertaking, needs joined up thinking with Borough Council How can we help facilitate | Support of greenway to Twyford railway station. Potential contribution if CIL available. Major infrastructure project can only lobby and possibly privide limited funding. | Unknown at this stage | Working Group (viability research)
Connectivity - Piggott School Cycle way | H | M | Med | May be easier than Charvil to Twyford cycleway with pressure on developers (riverways and Bridge farm) | Possible alternative and/or complement to Twyford Greenway | Unknown at this stage | Working Group (viability research)
Village Hall energy review | H | M | M | An energy review could include future heating/cooling solutions, solar panels and other energy saving measures | Feasibility study to explore options, costs and return on investment | Unknown at this stage | Working Group (viability research) | bar: 2026 Q4
Not approved/started
Underway/Consideration
Complete
Wokingham assets of interest
Playgrounds (Hawthorns) | H | M | Medium | WBC have equipment on order and should be fitted in October | bar: 2026 Q3
Playgrounds (Vale View) | M | L | Long | Would transfer maintenance liability | bar: 2026 Q3
Vale View Goal posts | H | H | Short | Cheap - missing keeps off main ptiches Trying to attange something with WBC | bar: 2026 Q3
Land options | H - to do list | H | Short | Chiltern Drive and cheviot close Worth pulling together a list of areas in short term | bar: 2028 Q3
EPF Pavilion | M | M | Long | Would make ownership simpler (not necessarily cheaper) if opportunity arose NEED TO AGREE PRINCIPLES IN SHORT TERM | bar: 2028 Q3
Green canopy |  |  |  | Picking up from Mike Heath work - improving green areas and taking opportunities as they arise Miranda to re-share Mike's work for consideration for including in NP
Completed Projects
East Park Farm - stream dredging | M | M | S | Work completed by Countryside Services |  | No cost | Amenities |  | 2026-05-26 | bar: 2027 Q2
Renovation of EPF playground |  |  |  |  | Completed |  |  |  | 2026-02-26 | bar: 2026 Q2
Village Hall Car Park Resurfacing |  |  |  |  | Completed | c £20k |  |  | 2025-10-25
Tennis Court Fencing |  |  |  |  | Replace link fencing |  |  |  | 2024-11-24
Updated Parish Council Website |  |  |  |  | Ongoing launch Q4 2024. Completed. |  |  |  | 2024-09-01
Additional Speed Indicator Device |  |  |  | Obtained | Purchased awaiting delivery. ***Delayed due to part shortage*** | £3k |  |  | 2024-08-01

## Maintenance Schedule 2026-30
Routine Maintenance Schedule for Village Hall and Pavilion
Village Hall
Activity | Last Done | Scheduled
Decorating | 2024 | 2029 | Every five years | Completed 2024
PAT test | 2026 | 2027 | Annual | Completed for 2026
Boiler Service | 2026 | 2027 | Annual
Fixed Wire Test | 2023 | 2028 | Every five years
Fire Servicing | 2026-07-01 | 2027-01-01 | Six Monthly | Last done Jul-26
Convector Heater service | 2025 | 2026 | Annual
Security System Service | 2025 | 2026 | Annual
Hall Floor resealing | 2024 | 2027 | Every three years | Completed 2024
Car Park Resurfacing | 2025 | ?
Curtains
East Park Farm and Pavilion
Activity | Last Done | Scheduled
Decorating | 2023 | 2028 | *
PAT test | 2026 | 2027 | Annual | Completed for 2026
Boiler Service | 2026 | 2027 | Annual | Completed for 2026
Fixed Wire Testing | 2022 | 2027 | Every Five Years
Fire Servicing | 2026-07-01 | 2026-01-01 | Six monthly | last done Jul-26
Shutters | 2026 | 2027 | Annual
Tennis Court maintenance | 2025 | 2030 |  | cleaned, repainted and sealed Jun-25
Football pitch remedial work | 2025 | 2026 | Annual | Completed for 2025
Tree maintenance | 2024 | 2027 |  | Lone Lime Tree Felled Dec-24
Playgrounds
Activity | Last Done | Scheduled
Rospa | 2026 | 2027 | Annual | Done for 2026